## MASTER
MASTER FEASIBILITY SUMMARY — All Phases ¦ 整地汇总
Green = cross-sheet formula ¦ Gray phase = indicative only, subject to planning approval and market review
| Phase 1 | Phase 2 | Phase 3
| Phase 1 精算 ✓ | Phase 2 概念 ◑ | Phase 3 TBC ○ | TOTAL | P1 %GDV | P2 %GDV | P3 %GDV
LAND & AREA
Net Developable Area (NDA)
Gross Floor Area (GFA sqft)
Nett Floor Area (NFA sqft)
Total Units (estimate)
GDV
Net GDV
GROSS DEVELOPMENT COST — 5 PILLARS
P1 · Land Cost
P2 · Construction
P3 · Infra + Stat
P4 · Professional
P5 · Finance + Mktg
GROSS DEVELOPMENT COST (GDC)
PROFIT BEFORE TAX (PBT)
KEY RATIOS & CHECKS
Profit Margin (PBT / Net GDV)
Land Cost / Net GDV
Construction Cost / Net GDV
⚠ Phase 3 numbers are INDICATIVE ONLY — pending planning approval and market study. Do not use for Board commitment.

## P1_INPUT
Phase 1 — High-rise Resi (精算) ¦ INPUT ASSUMPTIONS ¦ 状态：精算 — 已规划 ✓
Blue = hardcoded input ¦ Black = calculated ¦ Gray = TBC / indicative only
A · PROJECT INFORMATION
Phase Name | Phase 1 — High-rise Resi (精算)
Product Type | High-rise Residential
Target Launch Date | Mar 2025
Target VP Date | Dec 2027
Construction Period | 30 | months
B · AREA PARAMETERS
Net Developable Area (NDA) | 4 | acres | This phase's allocated NDA
Plot Ratio | 3.5 |  | Per planning approval / assumed
Gross Floor Area (GFA) |  | sqft | NDA × 43,560 × Plot Ratio
Efficiency Ratio | 0.78 | % | GFA → NFA sellable area
Nett Floor Area (NFA) — Sellable |  | sqft | Base for all psf calculations
Average Unit Size | 900 | sqft
Total Units (estimate) |  | units | NFA ÷ avg unit size
C · GDV ASSUMPTIONS
Average Selling Price (ASP) | 650 | RM psf NFA | Open market; based on market study
Bumi Quota % | 0.3 | % | Per DA conditions
Bumi Discount % | 0.07 | % | Applied to Bumi units only
Affordable / Low-cost % | 0.1 | %
Affordable Unit Price (RM/unit) | 42000 | RM/unit | Fixed by authority
Car Park Bays (extra sold) | 80 | bays
Car Park Price / Bay | 45000 | RM/bay
Gross GDV (open market) |  | RM | NFA × ASP
Less: Bumi Discount |  | RM | Bumi NFA × ASP × disc%
Less: Affordable Subsidy |  | RM | Units × aff% × (mkt−fixed price)
Car Park Revenue |  | RM
NET GDV |  | RM | Gross GDV − Bumi Discount − Affordable subsidy + Car Park

## P1_COSTING
Phase 1 — High-rise Resi (精算) ¦ GDC — 5 PILLARS COSTING ¦ 精算 — 已规划 ✓
C = Budget (RM) ¦ D = Committed ¦ E = Actual ¦ G = Budget psf NFA ¦ I = % of Net GDV
# | Cost Item | Budget (RM) | Committed (RM) | Actual (RM) | Variance | Budget psf | Actual psf | % Net GDV
P1 | PILLAR 1 · LAND COST | [6 empty] | Target: 15–25% Net GDV
1.1 | Land Purchase Price (this phase share) | 12000000 | 0 | 0 |  |  |  | Allocated by NDA % from master land cost
1.2 | Stamp Duty |  | 0 | 0 |  |  |  | Tiered 1/2/3/4%
1.3 | Legal Fees |  | 0 | 0 |  |  |  | ~1% of land price
1.4 | Conversion Premium | 500000 | 0 | 0 |  |  |  | Agri→Building; state authority
1.5 | Holding Interest (land loan) | 400000 | 0 | 0 |  |  |  | Land loan interest to launch
1.6 | Valuation + Misc |  | 0 | 0 |  |  |  | Valuer + misc legal
PILLAR 1 TOTAL
P2 | PILLAR 2 · CONSTRUCTION COST | [6 empty] | Target: 45–50% Net GDV
2.1 | Piling Works | 3200000 | 0 | 0 |  |  |  | Bored/driven per soil report
2.2 | Substructure | 2600000 | 0 | 0 |  |  |  | Foundation, pile caps, basement
2.3 | Superstructure — C&S | 15200000 | 0 | 0 |  |  |  | RC frame, beams, slabs
2.4 | Architectural Works | 8800000 | 0 | 0 |  |  |  | Façade, partitions, finishes
2.5 | M&E — Mechanical | 3600000 | 0 | 0 |  |  |  | HVAC, fire, lifts
2.6 | M&E — Electrical | 3000000 | 0 | 0 |  |  |  | LV/HV, lighting, ELV
2.7 | Plumbing & Sanitary | 1600000 | 0 | 0 |  |  |  | Water supply & sewerage
2.8 | Landscaping (Internal) | 800000 | 0 | 0 |  |  |  | Podium, pool, gym
2.9 | Preliminaries |  | 0 | 0 |  |  |  | ~8% of trade works
2.10 | Contingency (5%) |  | 0 | 0 |  |  |  | For approved VOs
PILLAR 2 TOTAL
P3 | PILLAR 3 · INFRASTRUCTURE + STATUTORY | [6 empty] | Target: 8–15% Net GDV
3.1 | Internal Roads | 1400000 | 0 | 0 |  |  |  | Tarmac, curbs, markings
3.2 | External Road (JKR) | 700000 | 0 | 0 |  |  |  | Off-site widening per JKR
3.3 | Drainage (JPS) | 880000 | 0 | 0 |  |  |  | Internal + tie-in to JPS
3.4 | TNB Substation | 600000 | 0 | 0 |  |  |  | Substation contribution + cabling
3.5 | Water Supply | 360000 | 0 | 0 |  |  |  | Pipe + reservoir contribution
3.6 | Sewerage (IWK) | 280000 | 0 | 0 |  |  |  | IWK connection / on-site STP
3.7 | Open Space + Amenities | 480000 | 0 | 0 |  |  |  | 10% site area; bus stop, surau
3.8 | Development Contribution | 1000000 | 0 | 0 |  |  |  | Cash to local authority (DA cond)
3.9 | Contingency (5%) |  | 0 | 0
PILLAR 3 TOTAL
P4 | PILLAR 4 · PROFESSIONAL FEES | [6 empty] | Target: 3–5% Net GDV
4.1 | Architect |  | 0 | 0 |  |  |  | ~4% of construction cost
4.2 | Structural Engineer |  | 0 | 0 |  |  |  | ~1.5% of C&S
4.3 | M&E Engineer |  | 0 | 0 |  |  |  | ~1.5% of M&E
4.4 | QS |  | 0 | 0 |  |  |  | ~1% of construction
4.5 | Land Surveyor | 30000 | 0 | 0 |  |  |  | Boundary + strata survey
4.6 | Town Planner | 60000 | 0 | 0 |  |  |  | DA/OSC liaison
4.7 | Geotech / SI | 80000 | 0 | 0 |  |  |  | Soil investigation
4.8 | Legal (SPA/APDL/Title) | 160000 | 0 | 0 |  |  |  | All project legal work
PILLAR 4 TOTAL
P5 | PILLAR 5 · FINANCE + MARKETING | [6 empty] | Target: 6–10% Net GDV
5.1 | Bridging Loan Interest (IDC) | 3800000 | 0 | 0 |  |  |  | Avg drawdown × rate × period
5.2 | Loan Arrangement + Legal |  | 0 | 0 |  |  |  | ~0.8% of loan facility
5.3 | Sales Gallery + Show Units | 700000 | 0 | 0 |  |  |  | Build, fitout, furnish
5.4 | Digital & Print Marketing | 320000 | 0 | 0 |  |  |  | Website, launches, print
5.5 | Agent Commission |  | 0 | 0 |  |  |  | ~2.5% Net GDV
5.6 | APDL + Developer Licence | 25000 | 0 | 0 |  |  |  | HDA fees
5.7 | Internal PM Allocation | 480000 | 0 | 0 |  |  |  | Team salary to project
5.8 | Insurance (CAR/PI/PL) |  | 0 | 0 |  |  |  | ~0.6% of construction
PILLAR 5 TOTAL
GDC | GROSS DEVELOPMENT COST
PBT | PROFIT BEFORE TAX (Net GDV − GDC)

## P1_CASHFLOW
PHASE 1 — DEVELOPMENT CASH FLOW & IRR
Yearly model · Blue = input · Black = calc · Green = link to P1_INPUT / P1_COSTING
ASSUMPTIONS & CURVES
| Σ / Param | Y0 | Y1 | Y2 | Y3 | Y4 | Notes
GDC spend curve (non-land) |  | 10% | 30% | 35% | 20% | 5% | Land booked Y0; rest follows construction S-curve
Revenue collection curve |  | 3% | 20% | 35% | 30% | 12% | Cash actually collected — drives inflow. Σ must = 100%
ref: HDA Sch.H billing |  | 10% | 30% | 35% | 20% | 5% | Statutory billing milestones (reference only)
ref: Sales take-up (RoS) |  | 20% | 35% | 25% | 15% | 5% | Units sold per year (reference only)
Discount rate (WACC) | 10% | [5 empty] | For NPV. Adjust to project hurdle / cost of capital
CASH OUTFLOW (RM)
Land Cost (P1) |  |  | 0 | 0 | 0 | 0
Development Cost (P2–P5)
TOTAL OUTFLOW
CASH INFLOW (RM)
Net GDV (link)
Revenue Collected
TOTAL INFLOW
NET CASH FLOW
Net Cash Flow
Cumulative Cash Flow
RETURNS
Project IRR (annual) | [6 empty] | Computes only if ≥1 negative year. HIGH here because land=4.9% of GDV + progress billing → tiny equity at risk. Read alongside Peak funding & NPV.
NPV @ WACC | [6 empty] | >0 = value-accretive
Years to turn cash-positive | [6 empty] | Approx payback in years
Peak funding need | [6 empty] | Most negative cumulative = max capital at risk
PBT (static) | [6 empty] | Net GDV − GDC
Profit margin | [6 empty] | PBT / Net GDV
⚠ CHECK: collection curve (row 7) Σ must = 100%; revenue B19 must ≈ Net GDV B18
NOTE: with so little land cost, the developer is nearly self-funding; project IRR overstates attractiveness — Peak funding need (B30) and NPV (B28) are the steadier signals.

## P2_INPUT
Phase 2 — High-rise Resi (概念) ¦ INPUT ASSUMPTIONS ¦ 状态：概念阶段 ◑
Blue = hardcoded input ¦ Black = calculated ¦ Gray = TBC / indicative only
A · PROJECT INFORMATION
Phase Name | Phase 2 — High-rise Resi (概念)
Product Type | High-rise Residential (Phase 2)
Target Launch Date | Q3 2026
Target VP Date | Dec 2028
Construction Period | 32 | months
B · AREA PARAMETERS
Net Developable Area (NDA) | 3.5 | acres | This phase's allocated NDA
Plot Ratio | 3.5 |  | Per planning approval / assumed
Gross Floor Area (GFA) |  | sqft | NDA × 43,560 × Plot Ratio
Efficiency Ratio | 0.78 | % | GFA → NFA sellable area
Nett Floor Area (NFA) — Sellable |  | sqft | Base for all psf calculations
Average Unit Size | 950 | sqft
Total Units (estimate) |  | units | NFA ÷ avg unit size
C · GDV ASSUMPTIONS
Average Selling Price (ASP) | 680 | RM psf NFA | Open market; based on market study
Bumi Quota % | 0.3 | % | Per DA conditions
Bumi Discount % | 0.07 | % | Applied to Bumi units only
Affordable / Low-cost % | 0.1 | %
Affordable Unit Price (RM/unit) | 42000 | RM/unit | Fixed by authority
Car Park Bays (extra sold) | 60 | bays
Car Park Price / Bay | 47000 | RM/bay
Gross GDV (open market) |  | RM | NFA × ASP
Less: Bumi Discount |  | RM | Bumi NFA × ASP × disc%
Less: Affordable Subsidy |  | RM | Units × aff% × (mkt−fixed price)
Car Park Revenue |  | RM
NET GDV |  | RM | Gross GDV − Bumi Discount − Affordable subsidy + Car Park

## P2_COSTING
Phase 2 — High-rise Resi (概念) ¦ GDC — 5 PILLARS COSTING ¦ 概念阶段 ◑
C = Budget (RM) ¦ D = Committed ¦ E = Actual ¦ G = Budget psf NFA ¦ I = % of Net GDV
# | Cost Item | Budget (RM) | Committed (RM) | Actual (RM) | Variance | Budget psf | Actual psf | % Net GDV
P1 | PILLAR 1 · LAND COST | [6 empty] | Target: 15–25% Net GDV
1.1 | Land Price (phase share) | 10500000 | 0 | 0 |  |  |  | Allocated from master land cost by NDA%
1.2 | Transaction costs (stamp/legal) |  | 0 | 0 |  |  |  | Stamp + legal ~5.5% of land price
1.3 | Conversion + Holding Interest | 1000000 | 0 | 0 |  |  |  | Combined estimate; refine at planning stage
PILLAR 1 TOTAL
P2 | PILLAR 2 · CONSTRUCTION COST | [6 empty] | Target: 45–50% Net GDV
2.1 | Main Building (C&S + Arch) | 23200000 | 0 | 0 |  |  |  | Estimated at RM 320 psf GFA
2.2 | M&E Complete | 7175000 | 0 | 0 |  |  |  | Estimated at RM 90 psf GFA
2.3 | Piling + Prelim + Contingency |  | 0 | 0 |  |  |  | ~15% of main works
PILLAR 2 TOTAL
P3 | PILLAR 3 · INFRASTRUCTURE + STATUTORY | [6 empty] | Target: 8–15% Net GDV
3.1 | Infrastructure Works | 3650000 | 0 | 0 |  |  |  | Roads, drainage, TNB, water — estimated
3.2 | Statutory Contributions | 1295000 | 0 | 0 |  |  |  | Open space + dev contribution — TBC at DA
3.3 | Contingency (5%) |  | 0 | 0
PILLAR 3 TOTAL
P4 | PILLAR 4 · PROFESSIONAL FEES | [6 empty] | Target: 3–5% Net GDV
4.1 | All Consultants (combined) | 450000 | 0 | 0 |  |  |  | Archi + Struct + ME + QS + Legal — estimated
PILLAR 4 TOTAL
P5 | PILLAR 5 · FINANCE + MARKETING | [6 empty] | Target: 6–10% Net GDV
5.1 | Finance Cost (IDC + fees) | 4600000 | 0 | 0 |  |  |  | Estimate; refine with loan term
5.2 | Marketing + Agent Commission |  | 0 | 0 |  |  |  | 2.5% agent + est. gallery/mktg
PILLAR 5 TOTAL
GDC | GROSS DEVELOPMENT COST
PBT | PROFIT BEFORE TAX (Net GDV − GDC)

## P3_INPUT
Phase 3 — Mixed TBC (占位) ¦ INPUT ASSUMPTIONS ¦ 状态：未规划 TBC ○
Blue = hardcoded input ¦ Black = calculated ¦ Gray = TBC / indicative only
A · PROJECT INFORMATION
Phase Name | Phase 3 — Mixed TBC (占位)
Product Type | Mixed / TBD
Target Launch Date | TBD
Target VP Date | TBD
Construction Period | 36 | months
B · AREA PARAMETERS
Net Developable Area (NDA) | 2.5 | acres | This phase's allocated NDA
Plot Ratio | 3 |  | Per planning approval / assumed
Gross Floor Area (GFA) |  | sqft | NDA × 43,560 × Plot Ratio
Efficiency Ratio | 0.75 | % | GFA → NFA sellable area
Nett Floor Area (NFA) — Sellable |  | sqft | Base for all psf calculations
Average Unit Size | 900 | sqft
Total Units (estimate) |  | units | NFA ÷ avg unit size
C · GDV ASSUMPTIONS
GDV per Nett Acre (benchmark) | 22000000 | RM/acre | From comparable completed projects in area
Estimated Gross GDV |  | RM | NDA × GDV/acre ¦ INDICATIVE ONLY
Bumi Discount Provision | 3000000 | RM | Flat provision; refine when planning known
NET GDV (indicative) |  | RM | TBC — pending planning & market study

## P3_COSTING
Phase 3 — Mixed TBC (占位) ¦ GDC — 5 PILLARS COSTING ¦ 未规划 TBC ○
C = Budget (RM) ¦ D = Committed ¦ E = Actual ¦ G = Budget psf NFA ¦ I = % of Net GDV
# | Cost Item | Budget (RM) | Committed (RM) | Actual (RM) | Variance | Budget psf | Actual psf | % Net GDV
P1 | PILLAR 1 · LAND COST (indicative) | [6 empty] | TBC
1.1 | Land Cost (NDA share) | 7500000 | 0 | 0 |  |  |  | Allocated from master by NDA%; TBC
1.2 | Transaction costs |  | 0 | 0 |  |  |  | Stamp + legal estimate
PILLAR 1 TOTAL
P2 | PILLAR 2 · CONSTRUCTION COST (indicative) | [6 empty] | TBC
2.1 | Construction (psf GFA estimate) | 111078000 | 0 | 0 |  |  |  | RM 300–380 psf GFA benchmark; TBC at design
PILLAR 2 TOTAL
P3 | PILLAR 3 · INFRASTRUCTURE + STATUTORY (indicative) | [6 empty] | TBC
3.1 | Infrastructure + Statutory |  | 0 | 0 |  |  |  | ~20% of construction; TBC at DA stage
PILLAR 3 TOTAL
P4 | PILLAR 4 · PROFESSIONAL FEES (indicative) | [6 empty] | TBC
4.1 | All Consultants |  | 0 | 0 |  |  |  | ~6% of construction; TBC
PILLAR 4 TOTAL
P5 | PILLAR 5 · FINANCE + MARKETING (indicative) | [6 empty] | TBC
5.1 | Finance + Marketing |  | 0 | 0 |  |  |  | ~8% Net GDV; TBC
PILLAR 5 TOTAL
GDC | GROSS DEV COST (INDICATIVE — TBC)
PBT | PROFIT (INDICATIVE — TBC)