## MASTER
MASTER FEASIBILITY SUMMARY — All Phases ¦ 整地汇总
Green = cross-sheet formula ¦ Gray phase = indicative only, subject to planning approval and market review
| Phase 1 | Phase 2 | Phase 3
| Phase 1 精算 ✓ | Phase 2 概念 ◑ | Phase 3 TBC ○ | TOTAL | P1 %GDV | P2 %GDV | P3 %GDV
LAND & AREA
Net Developable Area (NDA) | 4 | 3.5 | 2.5 | 10
Gross Floor Area (GFA sqft) | 609840 | 533610 | 326700 | 1470150
Nett Floor Area (NFA sqft) | 475675.2 | 416215.8 | 245025 | 1136916
Total Units (estimate) | 529 | 438 | 272 | 1239
GDV
Net GDV | 277571213.52 | 253447982.376 | 52000000 | 583019195.896 | 6939280338% | 7241370925% | 2080000000%
GROSS DEVELOPMENT COST — 5 PILLARS
P1 · Land Cost | 13532000 | 12077500 | 7912500 | 33522000 | 338300000% | 345071429% | 316500000%
P2 · Construction | 43999200 | 34931250 | 111078000 | 190008450 | 1099980000% | 998035714% | 4443120000%
P3 · Infra + Stat | 5985000 | 5192250 | 22215600 | 33392850 | 149625000% | 148350000% | 888624000%
P4 · Professional | 2856960 | 450000 | 6664680 | 9971640 | 71424000% | 12857143% | 266587200%
P5 · Finance + Mktg | 12880269.138 | 11616199.5594 | 4160000 | 28656468.6974 | 322006728% | 331891416% | 166400000%
GROSS DEVELOPMENT COST (GDC) | 79253429.138 | 64267199.5594 | 152030780 | 295551408.6974 | 28.55% | 25.36% | 292.4%
PROFIT BEFORE TAX (PBT) | 198317784.382 | 189180782.8166 | -100030780 | 287467787.1986 | 71.45% | 74.64% | -192.4%
KEY RATIOS & CHECKS
Profit Margin (PBT / Net GDV) | 71.45% | 74.64% | -192.4% | 49.31%
Land Cost / Net GDV | 4.875% | 4.765% | 15.22% | 5.75%
Construction Cost / Net GDV | 15.85% | 13.78% | 213.6% | 32.59%
⚠ Phase 3 numbers are INDICATIVE ONLY — pending planning approval and market study. Do not use for Board commitment.

## P1_INPUT
Phase 1 — High-rise Resi (精算) ¦ INPUT ASSUMPTIONS ¦ 状态：精算 — 已规划 ✓
Blue = hardcoded input ¦ Black = calculated ¦ Gray = TBC / indicative only
A · PROJECT INFORMATION
Phase Name | Phase 1 — High-rise Resi (精算)
Product Type | High-rise Residential
Target Launch Date | Mar 2025
Target VP Date | Dec 2027
Construction Period | 30 | months
B · AREA PARAMETERS
Net Developable Area (NDA) | 4 | acres | This phase's allocated NDA
Plot Ratio | 3.5 |  | Per planning approval / assumed
Gross Floor Area (GFA) | 609840 | sqft | NDA × 43,560 × Plot Ratio
Efficiency Ratio | 0.78 | % | GFA → NFA sellable area
Nett Floor Area (NFA) — Sellable | 475675.2 | sqft | Base for all psf calculations
Average Unit Size | 900 | sqft
Total Units (estimate) | 529 | units | NFA ÷ avg unit size
C · GDV ASSUMPTIONS
Average Selling Price (ASP) | 650 | RM psf NFA | Open market; based on market study
Bumi Quota % | 0.3 | % | Per DA conditions
Bumi Discount % | 0.07 | % | Applied to Bumi units only
Affordable / Low-cost % | 0.1 | %
Affordable Unit Price (RM/unit) | 42000 | RM/unit | Fixed by authority
Car Park Bays (extra sold) | 80 | bays
Car Park Price / Bay | 45000 | RM/bay
Gross GDV (open market) | 309188880 | RM | NFA × ASP
Less: Bumi Discount | -6492966.48 | RM | Bumi NFA × ASP × disc%
Less: Affordable Subsidy | -28724700 | RM | Units × aff% × (mkt−fixed price)
Car Park Revenue | 3600000 | RM
NET GDV | 277571213.52 | RM | Gross GDV − Bumi Discount − Affordable subsidy + Car Park

## P1_COSTING
Phase 1 — High-rise Resi (精算) ¦ GDC — 5 PILLARS COSTING ¦ 精算 — 已规划 ✓
C = Budget (RM) ¦ D = Committed ¦ E = Actual ¦ G = Budget psf NFA ¦ I = % of Net GDV
# | Cost Item | Budget (RM) | Committed (RM) | Actual (RM) | Variance | Budget psf | Actual psf | % Net GDV
P1 | PILLAR 1 · LAND COST | [6 empty] | Target: 15–25% Net GDV
1.1 | Land Purchase Price (this phase share) | 12000000 | 0 | 0 | 12000000 | 25.2273 | 0 | Allocated by NDA % from master land cost
1.2 | Stamp Duty | 464000 | 0 | 0 | 464000 | 0.97546 | 0 | Tiered 1/2/3/4%
1.3 | Legal Fees | 120000 | 0 | 0 | 120000 | 0.25227 | 0 | ~1% of land price
1.4 | Conversion Premium | 500000 | 0 | 0 | 500000 | 1.0511 | 0 | Agri→Building; state authority
1.5 | Holding Interest (land loan) | 400000 | 0 | 0 | 400000 | 0.84091 | 0 | Land loan interest to launch
1.6 | Valuation + Misc | 48000 | 0 | 0 | 48000 | 0.10091 | 0 | Valuer + misc legal
| PILLAR 1 TOTAL | 13532000 | 0 | 0 | 13532000 | 28.448 | 0 | 4.875%
P2 | PILLAR 2 · CONSTRUCTION COST | [6 empty] | Target: 45–50% Net GDV
2.1 | Piling Works | 3200000 | 0 | 0 | 3200000 | 6.7273 | 0 | Bored/driven per soil report
2.2 | Substructure | 2600000 | 0 | 0 | 2600000 | 5.4659 | 0 | Foundation, pile caps, basement
2.3 | Superstructure — C&S | 15200000 | 0 | 0 | 15200000 | 31.9546 | 0 | RC frame, beams, slabs
2.4 | Architectural Works | 8800000 | 0 | 0 | 8800000 | 18.5 | 0 | Façade, partitions, finishes
2.5 | M&E — Mechanical | 3600000 | 0 | 0 | 3600000 | 7.5682 | 0 | HVAC, fire, lifts
2.6 | M&E — Electrical | 3000000 | 0 | 0 | 3000000 | 6.3068 | 0 | LV/HV, lighting, ELV
2.7 | Plumbing & Sanitary | 1600000 | 0 | 0 | 1600000 | 3.3636 | 0 | Water supply & sewerage
2.8 | Landscaping (Internal) | 800000 | 0 | 0 | 800000 | 1.6818 | 0 | Podium, pool, gym
2.9 | Preliminaries | 3104000 | 0 | 0 | 3104000 | 6.5255 | 0 | ~8% of trade works
2.10 | Contingency (5%) | 2095200 | 0 | 0 | 2095200 | 4.4047 | 0 | For approved VOs
| PILLAR 2 TOTAL | 43999200 | 0 | 0 | 43999200 | 92.4984 | 0 | 15.85%
P3 | PILLAR 3 · INFRASTRUCTURE + STATUTORY | [6 empty] | Target: 8–15% Net GDV
3.1 | Internal Roads | 1400000 | 0 | 0 | 1400000 | 2.9432 | 0 | Tarmac, curbs, markings
3.2 | External Road (JKR) | 700000 | 0 | 0 | 700000 | 1.4716 | 0 | Off-site widening per JKR
3.3 | Drainage (JPS) | 880000 | 0 | 0 | 880000 | 1.85 | 0 | Internal + tie-in to JPS
3.4 | TNB Substation | 600000 | 0 | 0 | 600000 | 1.2614 | 0 | Substation contribution + cabling
3.5 | Water Supply | 360000 | 0 | 0 | 360000 | 0.75682 | 0 | Pipe + reservoir contribution
3.6 | Sewerage (IWK) | 280000 | 0 | 0 | 280000 | 0.58864 | 0 | IWK connection / on-site STP
3.7 | Open Space + Amenities | 480000 | 0 | 0 | 480000 | 1.0091 | 0 | 10% site area; bus stop, surau
3.8 | Development Contribution | 1000000 | 0 | 0 | 1000000 | 2.1023 | 0 | Cash to local authority (DA cond)
3.9 | Contingency (5%) | 285000 | 0 | 0 | 285000 | 0.59915 | 0
| PILLAR 3 TOTAL | 5985000 | 0 | 0 | 5985000 | 12.5821 | 0 | 2.156%
P4 | PILLAR 4 · PROFESSIONAL FEES | [6 empty] | Target: 3–5% Net GDV
4.1 | Architect | 1759968 | 0 | 0 | 1759968 | 3.6999 | 0 | ~4% of construction cost
4.2 | Structural Engineer | 228000 | 0 | 0 | 228000 | 0.47932 | 0 | ~1.5% of C&S
4.3 | M&E Engineer | 99000 | 0 | 0 | 99000 | 0.20813 | 0 | ~1.5% of M&E
4.4 | QS | 439992 | 0 | 0 | 439992 | 0.92498 | 0 | ~1% of construction
4.5 | Land Surveyor | 30000 | 0 | 0 | 30000 | 0.063068 | 0 | Boundary + strata survey
4.6 | Town Planner | 60000 | 0 | 0 | 60000 | 0.12614 | 0 | DA/OSC liaison
4.7 | Geotech / SI | 80000 | 0 | 0 | 80000 | 0.16818 | 0 | Soil investigation
4.8 | Legal (SPA/APDL/Title) | 160000 | 0 | 0 | 160000 | 0.33636 | 0 | All project legal work
| PILLAR 4 TOTAL | 2856960 | 0 | 0 | 2856960 | 6.0061 | 0 | 1.029%
P5 | PILLAR 5 · FINANCE + MARKETING | [6 empty] | Target: 6–10% Net GDV
5.1 | Bridging Loan Interest (IDC) | 3800000 | 0 | 0 | 3800000 | 7.9886 | 0 | Avg drawdown × rate × period
5.2 | Loan Arrangement + Legal | 351993.6 | 0 | 0 | 351993.6 | 0.73999 | 0 | ~0.8% of loan facility
5.3 | Sales Gallery + Show Units | 700000 | 0 | 0 | 700000 | 1.4716 | 0 | Build, fitout, furnish
5.4 | Digital & Print Marketing | 320000 | 0 | 0 | 320000 | 0.67273 | 0 | Website, launches, print
5.5 | Agent Commission | 6939280.338 | 0 | 0 | 6939280.338 | 14.5883 | 0 | ~2.5% Net GDV
5.6 | APDL + Developer Licence | 25000 | 0 | 0 | 25000 | 0.052557 | 0 | HDA fees
5.7 | Internal PM Allocation | 480000 | 0 | 0 | 480000 | 1.0091 | 0 | Team salary to project
5.8 | Insurance (CAR/PI/PL) | 263995.2 | 0 | 0 | 263995.2 | 0.55499 | 0 | ~0.6% of construction
| PILLAR 5 TOTAL | 12880269.138 | 0 | 0 | 12880269.138 | 27.0779 | 0 | 4.64%
GDC | GROSS DEVELOPMENT COST | 79253429.138 | 0 | 0 | 79253429.138 | 166.6125 | 0 | 28.55%
PBT | PROFIT BEFORE TAX (Net GDV − GDC) | 198317784.382 |  |  |  | 416.9185 |  | 71.45%

## P2_INPUT
Phase 2 — High-rise Resi (概念) ¦ INPUT ASSUMPTIONS ¦ 状态：概念阶段 ◑
Blue = hardcoded input ¦ Black = calculated ¦ Gray = TBC / indicative only
A · PROJECT INFORMATION
Phase Name | Phase 2 — High-rise Resi (概念)
Product Type | High-rise Residential (Phase 2)
Target Launch Date | Q3 2026
Target VP Date | Dec 2028
Construction Period | 32 | months
B · AREA PARAMETERS
Net Developable Area (NDA) | 3.5 | acres | This phase's allocated NDA
Plot Ratio | 3.5 |  | Per planning approval / assumed
Gross Floor Area (GFA) | 533610 | sqft | NDA × 43,560 × Plot Ratio
Efficiency Ratio | 0.78 | % | GFA → NFA sellable area
Nett Floor Area (NFA) — Sellable | 416215.8 | sqft | Base for all psf calculations
Average Unit Size | 950 | sqft
Total Units (estimate) | 438 | units | NFA ÷ avg unit size
C · GDV ASSUMPTIONS
Average Selling Price (ASP) | 680 | RM psf NFA | Open market; based on market study
Bumi Quota % | 0.3 | % | Per DA conditions
Bumi Discount % | 0.07 | % | Applied to Bumi units only
Affordable / Low-cost % | 0.1 | %
Affordable Unit Price (RM/unit) | 42000 | RM/unit | Fixed by authority
Car Park Bays (extra sold) | 60 | bays
Car Park Price / Bay | 47000 | RM/bay
Gross GDV (open market) | 283026744 | RM | NFA × ASP
Less: Bumi Discount | -5943561.624 | RM | Bumi NFA × ASP × disc%
Less: Affordable Subsidy | -26455200 | RM | Units × aff% × (mkt−fixed price)
Car Park Revenue | 2820000 | RM
NET GDV | 253447982.376 | RM | Gross GDV − Bumi Discount − Affordable subsidy + Car Park

## P2_COSTING
Phase 2 — High-rise Resi (概念) ¦ GDC — 5 PILLARS COSTING ¦ 概念阶段 ◑
C = Budget (RM) ¦ D = Committed ¦ E = Actual ¦ G = Budget psf NFA ¦ I = % of Net GDV
# | Cost Item | Budget (RM) | Committed (RM) | Actual (RM) | Variance | Budget psf | Actual psf | % Net GDV
P1 | PILLAR 1 · LAND COST | [6 empty] | Target: 15–25% Net GDV
1.1 | Land Price (phase share) | 10500000 | 0 | 0 | 10500000 | 25.2273 | 0 | Allocated from master land cost by NDA%
1.2 | Transaction costs (stamp/legal) | 577500 | 0 | 0 | 577500 | 1.3875 | 0 | Stamp + legal ~5.5% of land price
1.3 | Conversion + Holding Interest | 1000000 | 0 | 0 | 1000000 | 2.4026 | 0 | Combined estimate; refine at planning stage
| PILLAR 1 TOTAL | 12077500 | 0 | 0 | 12077500 | 29.0174 | 0 | 4.765%
P2 | PILLAR 2 · CONSTRUCTION COST | [6 empty] | Target: 45–50% Net GDV
2.1 | Main Building (C&S + Arch) | 23200000 | 0 | 0 | 23200000 | 55.7403 | 0 | Estimated at RM 320 psf GFA
2.2 | M&E Complete | 7175000 | 0 | 0 | 7175000 | 17.2387 | 0 | Estimated at RM 90 psf GFA
2.3 | Piling + Prelim + Contingency | 4556250 | 0 | 0 | 4556250 | 10.9468 | 0 | ~15% of main works
| PILLAR 2 TOTAL | 34931250 | 0 | 0 | 34931250 | 83.9258 | 0 | 13.78%
P3 | PILLAR 3 · INFRASTRUCTURE + STATUTORY | [6 empty] | Target: 8–15% Net GDV
3.1 | Infrastructure Works | 3650000 | 0 | 0 | 3650000 | 8.7695 | 0 | Roads, drainage, TNB, water — estimated
3.2 | Statutory Contributions | 1295000 | 0 | 0 | 1295000 | 3.1114 | 0 | Open space + dev contribution — TBC at DA
3.3 | Contingency (5%) | 247250 | 0 | 0 | 247250 | 0.59404 | 0
| PILLAR 3 TOTAL | 5192250 | 0 | 0 | 5192250 | 12.4749 | 0 | 2.049%
P4 | PILLAR 4 · PROFESSIONAL FEES | [6 empty] | Target: 3–5% Net GDV
4.1 | All Consultants (combined) | 450000 | 0 | 0 | 450000 | 1.0812 | 0 | Archi + Struct + ME + QS + Legal — estimated
| PILLAR 4 TOTAL | 450000 | 0 | 0 | 450000 | 1.0812 | 0 | 0.1776%
P5 | PILLAR 5 · FINANCE + MARKETING | [6 empty] | Target: 6–10% Net GDV
5.1 | Finance Cost (IDC + fees) | 4600000 | 0 | 0 | 4600000 | 11.052 | 0 | Estimate; refine with loan term
5.2 | Marketing + Agent Commission | 7016199.5594 | 0 | 0 | 7016199.5594 | 16.8571 | 0 | 2.5% agent + est. gallery/mktg
| PILLAR 5 TOTAL | 11616199.5594 | 0 | 0 | 11616199.5594 | 27.9091 | 0 | 4.583%
GDC | GROSS DEVELOPMENT COST | 64267199.5594 | 0 | 0 | 64267199.5594 | 154.4084 | 0 | 25.36%
PBT | PROFIT BEFORE TAX (Net GDV − GDC) | 189180782.8166 |  |  |  | 454.5257 |  | 74.64%

## P3_INPUT
Phase 3 — Mixed TBC (占位) ¦ INPUT ASSUMPTIONS ¦ 状态：未规划 TBC ○
Blue = hardcoded input ¦ Black = calculated ¦ Gray = TBC / indicative only
A · PROJECT INFORMATION
Phase Name | Phase 3 — Mixed TBC (占位)
Product Type | Mixed / TBD
Target Launch Date | TBD
Target VP Date | TBD
Construction Period | 36 | months
B · AREA PARAMETERS
Net Developable Area (NDA) | 2.5 | acres | This phase's allocated NDA
Plot Ratio | 3 |  | Per planning approval / assumed
Gross Floor Area (GFA) | 326700 | sqft | NDA × 43,560 × Plot Ratio
Efficiency Ratio | 0.75 | % | GFA → NFA sellable area
Nett Floor Area (NFA) — Sellable | 245025 | sqft | Base for all psf calculations
Average Unit Size | 900 | sqft
Total Units (estimate) | 272 | units | NFA ÷ avg unit size
C · GDV ASSUMPTIONS
GDV per Nett Acre (benchmark) | 22000000 | RM/acre | From comparable completed projects in area
Estimated Gross GDV | 55000000 | RM | NDA × GDV/acre ¦ INDICATIVE ONLY
Bumi Discount Provision | 3000000 | RM | Flat provision; refine when planning known
NET GDV (indicative) | 52000000 | RM | TBC — pending planning & market study

## P3_COSTING
Phase 3 — Mixed TBC (占位) ¦ GDC — 5 PILLARS COSTING ¦ 未规划 TBC ○
C = Budget (RM) ¦ D = Committed ¦ E = Actual ¦ G = Budget psf NFA ¦ I = % of Net GDV
# | Cost Item | Budget (RM) | Committed (RM) | Actual (RM) | Variance | Budget psf | Actual psf | % Net GDV
P1 | PILLAR 1 · LAND COST (indicative) | [6 empty] | TBC
1.1 | Land Cost (NDA share) | 7500000 | 0 | 0 | 7500000 | 30.6091 | 0 | Allocated from master by NDA%; TBC
1.2 | Transaction costs | 412500 | 0 | 0 | 412500 | 1.6835 | 0 | Stamp + legal estimate
| PILLAR 1 TOTAL | 7912500 | 0 | 0 | 7912500 | 32.2926 | 0 | 15.22%
P2 | PILLAR 2 · CONSTRUCTION COST (indicative) | [6 empty] | TBC
2.1 | Construction (psf GFA estimate) | 111078000 | 0 | 0 | 111078000 | 453.3333 | 0 | RM 300–380 psf GFA benchmark; TBC at design
| PILLAR 2 TOTAL | 111078000 | 0 | 0 | 111078000 | 453.3333 | 0 | 213.6%
P3 | PILLAR 3 · INFRASTRUCTURE + STATUTORY (indicative) | [6 empty] | TBC
3.1 | Infrastructure + Statutory | 22215600 | 0 | 0 | 22215600 | 90.6667 | 0 | ~20% of construction; TBC at DA stage
| PILLAR 3 TOTAL | 22215600 | 0 | 0 | 22215600 | 90.6667 | 0 | 42.72%
P4 | PILLAR 4 · PROFESSIONAL FEES (indicative) | [6 empty] | TBC
4.1 | All Consultants | 6664680 | 0 | 0 | 6664680 | 27.2 | 0 | ~6% of construction; TBC
| PILLAR 4 TOTAL | 6664680 | 0 | 0 | 6664680 | 27.2 | 0 | 12.82%
P5 | PILLAR 5 · FINANCE + MARKETING (indicative) | [6 empty] | TBC
5.1 | Finance + Marketing | 4160000 | 0 | 0 | 4160000 | 16.9779 | 0 | ~8% Net GDV; TBC
| PILLAR 5 TOTAL | 4160000 | 0 | 0 | 4160000 | 16.9779 | 0 | 8%
GDC | GROSS DEV COST (INDICATIVE — TBC) | 152030780 |  |  |  | 620.4705 |  | 292.4%
PBT | PROFIT (INDICATIVE — TBC) | -100030780 | [5 empty] | -192.4%